## Sue Saupe concerns
allow units to display at greater extents?
nautical charts, bathymetry?
rendering of Habitat, etc. | Steve will do?

## Sheet2
post-meeting
3D Units
initial zoom tilted so sky not visible?
modify 3D extent function to handle when sky is visible
message to zoom in when not getting all features
help on map navigation?
groupdataextract available at .5 or 1X scale of Chichagof
when sorted on a column, mouseover on a row still brings up the same popup
fix formatting of unit table
message for download failure
back-up to previous dialog
photo marker skips through when there is a discontinuity
Dutch Harbor issue
not there any more?
(figure out multiple copies of unit graphic objects)
try to get 3D version? (maybe not that high-priority)
[query layers and alternate layout are not high-priority]
Add checkbox to turn unit display on/off, default to off
prevent panning when highlighting graphic object that extends beyound current view
only create graphics that are entirely within view?
use polylines (instead of unit envelopes) to display units (maybe line for selected, envelope for background)
lighter envelope background
degree symbols in photo/video headers
tooltips for unit field values
4.5 version loses line breaks in map popups
Unit query failure -- was due to missing rendering for a layer
get CMECS on site
darker/bolder fonts
smaller video point graphics
NOAA colors
hide middle panel
add tab for 3D Units site
unit table not always showing all fields
download: add video clips
hide graphic selection marker when zoomed out, or when "show unit markers" is turned off
consistent order of unit table columns

## layers show issue
bug: | layers=show:-1 | 4.3
| layers=show:3 | 4.5

## Sheet1
identify areas that could be debugged by Tristan?
try site on 1and1.com with iPad
offline app
GP service: storage estimate
make panel for OfflineApp widget, with more info & choices
CSS: Use "em" or "rem" instead of "px" for units, to scale with device size
or just use minimum size? (24px?)

## Devices
Browser:
Device | Chrome | Safari | FireFox | IE | Edge
Windows desktop
Windows laptop
Macbook Pro
iPad Mini
Xoom tablet
iPod Touch
OfflineLink widget is messing up iOS
with OfflineLink disabled, video queuing/playback is still not working

## questions
Questions for Steve:
Does PSMFC server have streaming video yet?
(and photos)

## API wish list
ArcGIS JavaScript API 4.x wishlist
esri/views/MapView |  | get mouse pointer to point correctly
position indicated by pointer is maybe 10 pixels SE of actual point?
(or else hitTest is inaccurate)
| hitTest method | What is search tolerance?
Can this be set/read?
esri/widgets/LayerList |  | start expanded? (check first)
esri/widgets/Locate |  | add parameter to set the scale to zoom to
esri/widgets/Popup |  | prevent popup from changing map extent | There is a reposition() function, but have to figure out how to respond to Popup "show" event
shift popup box position as needed to fit within the map frame, rather than panning to fit the box